Independent Monitoring Association for Child Labour (IMAC)

#### Sixty Third Progress Report

(01 June 2008 –   30 June 2008)

General:

Since the beginning of the programme, so far, in total 135 sports ball manufacturers joined the Child Labour Elimination Programme (CLEP). However 50 manufacturers had left the programme on different occasions due to the non-payment of their dues to the SCCI or some other reasons. As such 85 soccer ball manufacturers are present in the programme at the moment. From this, 62 manufacturers are in IMAC’s main database whereas 23 are in the provisional list.

Monitoring Progress:

During the month of June 2008 there were 2,734 stitching centers operational and registered with IMAC. Of these IMAC monitored 1,524 stitching centers pertaining to 53 manufacturers. This included 9 manufacturers from the list of provisional members. Altogether 23 manufacturers are in the provisional list. Among the 23 provisional members, 12 manufacturers are not active as they do not have any work in hand and their monitoring is stopped.

Of the total 2,734 operational centers, 397 were small village-based centers, 1,006 were exclusively female centers, 346 were combined and rest of the 985 centers were male centers. During June 2008, out of the 1,524 centers visited, 508 were male centers, 601 were female centers, 169 were combined and 246 were small village based centers. While visiting the stitching centres outside Sialkot district, the IMAC monitored 194 centers of 22 manufacturers with 1,699 stitchers located in the districts of Gujranwala, Gujrat, Narowal, Hafiz Abad and Sheikhupura.

Based on the IMAC criterion of ABC performance list, 60 manufacturers, are placed in the category “A”, two manufacturers i.e. M/S Orpheus Enterprises (Pvt) Ltd. and M/S Estrella International maintained their status in Category “C”, whereas one manufacturer M/S Mallhi Sports has been removed from the program due to serious violations.

In the month of June 2008 one new manufacturer M/S Matass Sports joined the program and one manufacturer M/S Astra Sports Articles (Pvt) Ltd. rejoined the program.

Working Conditions in the Stitching Centres Monitored by IMAC Monitors:

During the regular monitoring of the stitching centres, the IMAC monitoring teams also try to assess the physical conditions at the stitching centers such as sufficient sitting space for stitchers, light, sitting arrangements, ventilation/ air circulation, drinking water availability and toilets. However, while collecting these information cultural norms and social aspects are kept in view.  Generally three categories are used for these assessment: 1:  Excellent/ More than sufficient, 2:  Good/ sufficient; 3: Poor/ insufficient/not available. The stitching centres are classified into two types i.e. Purposely Built Centres and others. The Purposely Built Centres are monitored for two additional conditions i.e. Fire Extinguisher and First Aid facilities. As a policy measure, IMAC does not monitor working conditions of house based stitching centres. Therefore, 246 village based / house based centres visited in June 2008 are excluded for monitoring working conditions. As such, for working conditions, IMAC monitors monitored 1,278 stitching centres.

Of these, IMAC monitors found 694 stitching centres either closed due to variety of reasons or found stitchers sitting idle as at the time of the visit the stitchers did not have enough material to stitch. As such IMAC monitors could verify the working conditions of only 584 centres. The details of the working conditions of the centres observed in the monitoring visits are given in the following paragraphs:

Space:	430 stitching centres visited had more than enough space and 154 had enough space.

Problems: None

Lights:	396 stitching centres were well lit whereas 188 stitching centres had reasonably good lighting system such as bulbs and windows.

Problems: None

Ventilation:	374 stitching centres were found having good ventilation and air circulation system like high roofs, large doors and windows; 210 stitching centres had somewhat average conditions.

Problems: None

Drinking

Water:           	584 stitching centres had drinking water available to the stitchers.

Problems: None

Toilets:	472 stitching centres had proper toilets facilities i.e. one toilet available for thirty stitchers; at 112 stitching centres toilets were available but not sufficient.

Problems:  None

Sitting

Arrangement:  In 417 centres, the sitting arrangement was good i.e. the stitchers were using a chair or a chowki and mat, at 167 centres stitchers were sitting on a chaoki.

Problems: None

General

Hygiene:	201 centers were found in good hygienic conditions whereas in 383 centres, the hygienic conditions were average.

Problems:  None

Fire

Extinguisher:  	IMAC monitors visited 63 centres, purposely built by the manufacturers, out of which 62 centres had fire extinguishers.

Problems: 1 stitching centres had no such facility.

First Aid:	Out of 63 purposely-built centres, in 47 stitching centres first aid box was available in case of emergencies and the stitchers or the subcontractor knew how to use it. 15 centres have such facility but no one knew how to use it.

Problems: 1 stitching centres had no such facility.

Violations Identified During June 2008:

In the month of June 2008, respective manufacturers were asked for explanation about the violations of the programme provisions, as follows:

- 4 Manufacturers for the suspicion of child labour involvement.

- 26 Manufacturers for Un-registered stitching activities.

- 10 Manufacturers for non-printing of ID Code.

- 1 Manufacturer for poor working conditions.

Responses of Manufacturers on violations identified During June 2008:

- Child Labour:

Problems: During June 2008, 4 manufacturers were identified at the suspicion of child labour 			        involvement.

Response:

  - 2 Manufacturers have provided age proof showing that the suspected children were fulfilling the minimum age criteria.

  - 1 Manufacturer replied that the mentioned work did not belong to him.

  - Reply from 1 Manufacturer is awaited.

- Un-registered Stitching Activities:

Problems: During June 2008, 26 manufacturers were identified with un-registered stitching activities.

Responses received so far are as follows:

  - 2 Manufacturers admitted that the material was leaked from the registered centres. These manufacturers took strict actions against the sub-contractor(s) who had leaked out the material and stopped working with the sub-contractor(s).

  - 20 Manufacturers have issued warnings to their sub-contractor(s) responsible for the violation.

  - 1 Manufacturer replied that the mentioned work did not belong to him.

  - Responses from remaining 2 Manufacturers are awaited.

- Non-printing of ID Code:

Problems: During June 2008, 10 Manufacturer were identified with non-printing of ID Codes.

Responses:

  - 5 Manufacturers confirmed that it happened due to negligence of their printing staff who have been censured for the same.

  - 1 Manufacturer replied that the mentioned material did not belong to him.

  - Responses from remaining 4 Manufacturers are awaited

- Working Conditions:

Problems: During June 2008, 1 manufacturer was  identified having poor working conditions at their 		     stitching centre.

Responses:

  - This manufacturer has cleared the complaints regarding poor working conditions.

Remaining responses of  May 2008:

- Child Labour:

- 2 Manufacturers took strict actions against the sub-contractor(s) and terminated the contract with

them.

- Un-registered Stitching Activities:

- 3  Manufacturers did not respond. Reminders have been issued to them.

- 7  Manufacturers have issued warnings to their sub-contractor(s) responsible for the violation.

- 1  Manufacturer replied that the mentioned work did not belong to him.